## Hours estimate
Data Security Envisioning Workshop |  |  |  |  | Data Security Check - Mandatory Scope
Estimated partner effort |  |  |  |  | Estimated partner effort - Mandatory Scope
|  |  | Delivery |  |  |  |  | Delivery
| Pre-engagement call |  | 1.5 |  |  | Step 1 | Kick-off meeting
| Data Security Check - default scope |  | 22.7 |  |  |  | Core Activities | 1.5
| Present & discuss the Data Security Check findings |  | 2 |  |  |  | Exchange Online | 0.5
| Microsoft Purview portfolio overview |  | 2 |  |  |  | SharePoint Online | 0.5
| Recommendations and next steps |  | 2 | + |  |  | Teams | 0.5
| Total Estimated partner effort |  | 30.2 |  |  |  | Insider Risk Management | 1
[6 empty] | Step 2 | Acquire and assign licenses
[7 empty] | Core Activities | 0.5
Data Security Envisioning Workshop - TO BE USED IN STATEMENT OF WORK | [6 empty] | Exchange Online | 0
Estimated partner effort | [6 empty] | SharePoint Online | 0
|  |  | Delivery |  |  |  | Teams | 0
| Pre-engagement call |  | 1.5 |  |  |  | Insider Risk Management | 0
| Data Security Check - default scope |  | 22.7 |  |  | Step 3 | Setup and Configuration
| Select included module. |  | x.x Hrs |  |  |  | Core Activities | 1
| Present & discuss the Data Security Check findings |  | 2 |  |  |  | Exchange Online | 1
| Microsoft Purview portfolio overview |  | 2 |  |  |  | SharePoint Online | 1
| Recommendations and next steps |  | 2 | + |  |  | Teams | 1
| Total Estimated partner effort |  | 30.2 |  |  |  | Insider Risk Management | 2
[6 empty] | Step 4 | Analyze the findings
[7 empty] | Core Activities | 0
[7 empty] | Exchange Online | 1
[7 empty] | SharePoint Online | 1
[7 empty] | Teams | 1
[7 empty] | Insider Risk Management | 1.5
[6 empty] | Step 5 | Report and recommendations write-up
[7 empty] | Core Activities | 1.5
[7 empty] | Exchange Online | 1
[7 empty] | SharePoint Online | 1
[7 empty] | Teams | 1
[7 empty] | Insider Risk Management | 1
[6 empty] | Step 6 | Decommision
[7 empty] | Core Activities | 0.2
[7 empty] | Exchange Online | 0.5
[7 empty] | SharePoint Online | 0.5
[7 empty] | Teams | 0.5
[7 empty] | Insider Risk Management | 0.5 | +
[6 empty] | Estimated effort |  | 22.7
Data Security Check - MANDATORY MODULE |  |  |  |  | Data Security Check - MANDATORY MODULE |  |  |  |  | Data Security Check - MANDATORY MODULE |  |  |  |  | Data Security Check - MANDATORY MODULE |  |  |  |  | Data Security Check - Optional Scope - overview for the Master Delivery guide
Exchange Online |  |  |  |  | SharePoint Online |  |  |  |  | Teams |  |  |  |  | Insider Risk Management |  |  |  |  | Estimated partner effort - Optional Scope
|  |  | Delivery |  |  |  |  | Delivery |  |  |  |  | Delivery |  |  |  |  | Delivery |  | Compliance Manager |  |  | Delivery |  | Windows endpoints |  |  | Delivery
| Step 1 | Additional effort - Kick-off meeting | 0.5 |  |  | Step 1 | Additional effort - Kick-off meeting | 0.5 |  |  | Step 1 | Additional effort - Kick-off meeting | 0.5 |  |  | Step 1 | Additional effort - Kick-off meeting | 1 |  |  | Step 1 | Kick-off meeting |  |  |  | Step 1 | Kick-off meeting
| Step 2 | Additional effort - Acquire and assign licenses |  |  |  | Step 2 | Additional effort - Acquire and assign licenses |  |  |  | Step 2 | Additional effort - Acquire and assign licenses |  |  |  | Step 2 | Additional effort - Acquire and assign licenses |  |  |  |  | Additional effort - Compliance Manager | 0.5 |  |  |  | Additional effort - Windows endpoints | 1
| Step 3 | Additional effort - Setup and Configuration | 1 |  |  | Step 3 | Additional effort - Setup and Configuration | 1 |  |  | Step 3 | Additional effort - Setup and Configuration | 1 |  |  | Step 3 | Additional effort - Setup and Configuration | 2 |  |  | Step 2 | Acquire and assign licenses |  |  |  | Step 2 | Acquire and assign licenses
| Step 4 | Additional effort - Analyze the findings | 1 |  |  | Step 4 | Additional effort - Analyze the findings | 1 |  |  | Step 4 | Additional effort - Analyze the findings | 1 |  |  | Step 4 | Additional effort - Analyze the findings | 1.5 |  |  |  | Additional effort - Compliance Manager | 0 |  |  |  | Additional effort - Windows endpoints | 0
| Step 5 | Additional effort - Report and recommendations write-up | 1 |  |  | Step 5 | Additional effort - Report and recommendations write-up | 1 |  |  | Step 5 | Additional effort - Report and recommendations write-up | 1 |  |  | Step 5 | Additional effort - Report and recommendations write-up | 1 |  |  | Step 3 | Setup and Configuration |  |  |  | Step 3 | Setup and Configuration
| Step 6 | Additional effort - Decommision | 0.5 |  |  | Step 6 | Additional effort - Decommision | 0.5 |  |  | Step 6 | Additional effort - Decommision | 0.5 |  |  | Step 6 | Additional effort - Decommision | 0.5 |  |  |  | Additional effort - Compliance Manager | 1 |  |  |  | Additional effort - Windows endpoints | 4.5
|  |  |  | + |  |  |  |  | + |  |  |  |  | + |  |  |  |  | + |  | Step 4 | Analyze the findings |  |  |  | Step 4 | Analyze the findings
| Estimated additional effort |  | 4 |  |  | Estimated additional effort |  | 4 |  |  | Estimated additional effort |  | 4 |  |  | Estimated additional effort |  | 6 |  |  |  | Additional effort - Compliance Manager | 1 |  |  |  | Additional effort - Windows endpoints | 1
[21 empty] | Step 5 | Report and recommendations write-up |  |  |  | Step 5 | Report and recommendations write-up
Data Security Check - OPTIONAL MODULE |  |  |  |  | Data Security Check - OPTIONAL MODULE |  |  |  |  | Data Security Check - OPTIONAL MODULE |  |  |  |  | Data Security Check - OPTIONAL MODULE | [6 empty] | Additional effort - Compliance Manager | 1 |  |  |  | Additional effort - Windows endpoints | 1
Compliance Manager |  |  |  |  | On-premises data scanner |  |  |  |  | Windows endpoints |  |  |  |  | Communication Compliance | [5 empty] | Step 6 | Decommision |  |  |  | Step 6 | Decommision
|  |  | Delivery |  |  |  |  | Delivery |  |  |  |  | Delivery |  |  |  |  | Delivery |  |  |  | Additional effort - Compliance Manager | 0.5 |  |  |  | Additional effort - Windows endpoints | 0.5
| Step 1 | Additional effort - Kick-off meeting | 0.5 |  |  | Step 1 | Additional effort - Kick-off meeting | 0.5 |  |  | Step 1 | Additional effort - Kick-off meeting | 1 |  |  | Step 1 | Additional effort - Kick-off meeting | 0.5 | [5 empty] | + |  |  |  |  | +
| Step 2 | Additional effort - Acquire and assign licenses |  |  |  | Step 2 | Additional effort - Acquire and assign licenses |  |  |  | Step 2 | Additional effort - Acquire and assign licenses |  |  |  | Step 2 | Additional effort - Acquire and assign licenses | 0 |  |  | Estimated additional effort - Compliance Manager |  | 4 |  |  | Estimated additional effort - Windows endpoints |  | 8
| Step 3 | Additional effort - Setup and Configuration | 1 |  |  | Step 3 | Additional effort - Setup and Configuration | 4 |  |  | Step 3 | Additional effort - Setup and Configuration | 4.5 |  |  | Step 3 | Additional effort - Setup and Configuration | 1
| Step 4 | Additional effort - Analyze the findings | 1 |  |  | Step 4 | Additional effort - Analyze the findings | 1.5 |  |  | Step 4 | Additional effort - Analyze the findings | 1 |  |  | Step 4 | Additional effort - Analyze the findings | 1 |  | On-premises data scanner |  |  | Delivery |  | Communication Compliance |  |  | Delivery
| Step 5 | Additional effort - Report and recommendations write-up | 1 |  |  | Step 5 | Additional effort - Report and recommendations write-up | 1.5 |  |  | Step 5 | Additional effort - Report and recommendations write-up | 1 |  |  | Step 5 | Additional effort - Report and recommendations write-up | 1 |  |  | Step 1 | Kick-off meeting |  |  |  | Step 1 | Kick-off meeting
| Step 6 | Additional effort - Decommision | 0.5 |  |  | Step 6 | Additional effort - Decommision | 0.5 |  |  | Step 6 | Additional effort - Decommision | 0.5 |  |  | Step 6 | Additional effort - Decommision | 0.5 |  |  |  | Additional effort - On-premises data scanner | 0.5 |  |  |  | Additional effort - Communication Compliance | 0.5
|  |  |  | + |  |  |  |  | + |  |  |  |  | + |  |  |  |  | + |  | Step 2 | Acquire and assign licenses |  |  |  | Step 2 | Acquire and assign licenses
| Estimated additional effort |  | 4 |  |  | Estimated additional effort |  | 8 |  |  | Estimated additional effort |  | 8 |  |  | Estimated additional effort |  | 4 |  |  |  | Additional effort - On-premises data scanner | 0 |  |  |  | Additional effort - Communication Compliance | 0
[21 empty] | Step 3 | Setup and Configuration |  |  |  | Step 3 | Setup and Configuration
Data Security Check - OPTIONAL MODULE | [21 empty] | Additional effort - On-premises data scanner | 4 |  |  |  | Additional effort - Communication Compliance | 1
Data security for AI | [20 empty] | Step 4 | Analyze the findings |  |  |  | Step 4 | Analyze the findings
|  |  | Delivery | [18 empty] | Additional effort - On-premises data scanner | 1.5 |  |  |  | Additional effort - Communication Compliance | 1
| Step 1 | Additional effort - Kick-off meeting | 1 | [17 empty] | Step 5 | Report and recommendations write-up |  |  |  | Step 5 | Report and recommendations write-up
| Step 2 | Additional effort - Acquire and assign licenses | 0 | [18 empty] | Additional effort - On-premises data scanner | 1.5 |  |  |  | Additional effort - Communication Compliance | 1
| Step 3 | Additional effort - Setup and Configuration | 4.5 | [17 empty] | Step 6 | Decommision |  |  |  | Step 6 | Decommision
| Step 4 | Additional effort - Analyze the findings | 1 | [18 empty] | Additional effort - On-premises data scanner | 0.5 |  |  |  | Additional effort - Communication Compliance | 0.5
| Step 5 | Additional effort - Report and recommendations write-up | 1 | [20 empty] | + |  |  |  |  | +
| Step 6 | Additional effort - Decommision | 0.5 | [17 empty] | Estimated additional effort - On-premises data scanner |  | 8 |  |  | Estimated additional effort - Communication Compliance |  | 4
+
| Estimated additional effort |  | 8 | [16 empty] | Data security for AI |  |  | Delivery
[21 empty] | Step 1 | Kick-off meeting
[22 empty] | Data security for AI | 1
[21 empty] | Step 2 | Acquire and assign licenses
[22 empty] | Data security for AI | 0
[21 empty] | Step 3 | Setup and Configuration
[22 empty] | Data security for AI | 4.5
[21 empty] | Step 4 | Analyze the findings
[22 empty] | Data security for AI | 1
[21 empty] | Step 5 | Report and recommendations write-up
[22 empty] | Data security for AI | 1
[21 empty] | Step 6 | Decommision
[22 empty] | Data security for AI | 0.5
+
[21 empty] | Estimated additional effort - Data security for AI |  | 8

## Version information
Version | Date | Author | Changes | Steps and step names | [5 empty] | Module | Hours
1.0 | November 2019 | François van Hemert | First published v1 release | Step 1 | Additional effort - Kick-off meeting | Core Activities | Kick-off meeting | Estimated additional effort for preparation | Additional effort - | Select included module. | x.x Hrs
2.0 | June 2020 | François van Hemert | First published v2 release | Step 2 | Additional effort - Acquire and assign licenses | Core Activities | Acquire and assign licenses | Estimated additional effort for delivery |  | Compliance Manager | 4
2.1 | 2020-11-01 | François van Hemert | Maintenance release, minor updates. | Step 3 | Additional effort - Setup and Configuration | Core Activities | Setup and Configuration | Estimated total effort |  | On-premises data scanner | 8
3.0 | January 2021 | François van Hemert | Modular release, added Compliance Manager, removed CIE | Step 4 | Additional effort - Analyze the findings | Core Activities | Analyze the findings |  |  | Windows endpoints | 8
3.1 | February 2021 | François van Hemert | Added Teams Data Loss Prevention as optional module | Step 5 | Additional effort - Report and recommendations write-up | Core Activities | Report and recommendations write-up |  |  | Communication Compliance | 4
4.0 | June 2021 | François van Hemert | Workshop split, update to align with new narrative, rebranding, updates to guidance and organized around data repositories. | Step 6 | Additional effort - Decommision | Core Activities | Decommision |  |  | Purview for AI | 8
4.1 | October 2021 | François van Hemert | Update with Compliance Manager Premium Assessments
4.2 | 2022-07-01 | François van Hemert | Purview branding update, step-by-step guidance update to align with changes M365
4,2,2 | 2023-01-01 | François van Hemert | Updated version number to align with kit, no content updates
6.0 | 2023-08-01 | François van Hemert | Workshop merge, align with FY24 solution play.
6.5 | Juli 2024 | François van Hemert | Update step guidance, align with FY25 solution play
6.6 | 2024-10-01 | François van Hemert | Version number update for alignment, no content changes
7.0 | 2025-01-01 | François van Hemert | Added Data security for generative AI module
7.1 | 2025-05-01 | François van Hemert | Version number update, no further changes
8.0 | Juli 2025 | François van Hemert | Update to align with current product features and functionality (evergreen), update name, update branding.
8.5 | 2026-01-01 | François van Hemert | Version number update, no further changes